## Sheet1
SILIGURI JALPAIGURI DEVELOPMENT AUTHORITY Report for display hoarding of advertisement at different locations around Siliguri Report as on 10.03.2023
Sl No. | Location | Name of the engaged agency | Work order issued to the agency | Contract period | Contract value | Amount received as per contract value | Present status
1 | Advertisement display hoarding at Uttarapan market complex at Hill Cart Road, Siliguri. | -------------- | ------------------ | --------------- | --------------- | --------------- | NIB (E-BIDDING) No. 13 / Hoarding / Uttarapan / 22-23, Vide memo no. 1648 /i Admn / 821/ 22/ SJDA, dated 26.09.2022 has been circulated. Last date of the opening of BID was 21.10.2022. Tender section submitted current status of the NIB. One bidder has been participated. File placed to Tender Section for Re-tender on 25/11/22. As per NIB No.13 / Hoarding / Uttarapan / 22-23 (2nd call), 02nos. bidder has been participated. 3rd call to be floated.
2 | Advertisement display at Street Light Poles along the flyover at Mahabirsthan | COLOURS, Siliguri | 262/SJDA dt.06/02/2020 terminated vide no.703/SJDA dt.28/04/2022 | Work order terminated | Rs. 16,87,400/- | Rs. 8,52,542/- | 1. Demand letter to COLOURS issued vide memo no.1614/SJDA dt.22/09/22 for outstanding balance amount for Rs.8,51,542/- only. 2. NIB (E-BIDDING) No. 05 / Hoarding / Flyover / 22-23,(2nd call), Vide memo no. 1662 /I/Admn/316/15/SJDA, dated 27.09.2022 has been circulated. Last date of the opening of BID was 01.11.2022.File placed to tender section for current status of the NIB. No one has been participated in the NIB. Re-tender (3rd call) was floated. No one has been participated. 4th call to be floated.
3 | Advertisement display hoarding Entrance & Exit gate of flyover at Mahabirsthan (3 no. Display board) | -------------- | ----------------- | --------------- | --------------- | --------------- | NIB (E-BIDDING) No. 11 / Hoarding / Entrance / 22-23, Vide memo no. 1650 /I Admn / 822/22/ SJDA, dated 26.09.2022 has been circulated. Last date of the opening of BID was 21.10.2022. Tender section submitted current status of the NIB. One bidder has been participated. File placed to Tender Section for Re-tender on 25/11/22. As per NIB No.11 / Hoarding/ Entrance / 22-23 (2nd call), 02nos bidder has been participated. 3rd call to be floated.
4 | Advertisement display Glow Sign Board at Air View More, Jalpai More, Panitanki More and Venus More | -------------- | --------------- | ------------ | ------------- | --------------- | NIB (E-BIDDING) No. 16 / Hoarding / Traffic/ 22-23, Vide memo no. 1677 / I / Admn / 825/22/ SJDA, dated 28.09.2022 has been circulated. Last date of the opening of BID was 21.10.2022. Tender section submitted current status of the NIB. One bidder has been participated. File placed to Tender Section for Re-tender on 25/11/22. Re-tender (2nd call) was floated. 02 nos bidder has been participated. 3rd call to be floated.
5 | Glow Sign Board at - 1. Church road- Bidhan road 2. Jhankar more 3. Darjeeling more 4.Champasari more 5. Khaprail more 6. Sevoke road & champasari road junction 7. Near Payal Cinema hall 8. Junction point of Pranami Mandir & Sevoke road 9. Vishal cinema more. 10. Asigarh more ( Eastern By Pass & Ghugumali connect) | ----------- | ---------- | ---------- | ---------- | ------- | NIB (E-BIDDING) No. 14/ Signboard / Traffic/ 22-23, Vide memo no. 1649 / I/ Admn /823/22/ SJDA, dated 26.09.2022 has been circulated. Last date of the opening of BID was 21.10.2022. Tender section submitted current status of the NIB. One bidder has been participated. Re-tender (2nd call) was floated. 02 nos bidder has been participated. 3rd call to be floated.
6 | Advertisement display Hoarding at Fulbari (near Patha Sathi) | -------------- | ------------------- | -------------- | ---------------- | --------------- | NIB (E-BIDDING) No. 12/ Hoarding / Pathasathi/ 22-23, Vide memo no. 1647 /I / Admn / 820/ 22 / SJDA, dated 26.09.2022 has been circulated. Last date of the opening of BID was 21.10.2022. Tender section submitted current status of the NIB. One bidder has been participated. File placed to Tender Section for Re-tender on 25/11/22. As per NIB No.13 / Hoarding / Pathasathi / 22-23 (2nd call), 02 nos. bidder has been participated. 3rd call to be floated.
7 | Installation advertisement board at 176 nos. LED Light poles located near Salbari Bazar, from DPS School to Siliguri Institute of Technology (SIT). | ------------ | -------------- | ----------- | ------------- | --------------- | NIB (E-BIDDING) No. 006/ ADMN/ 22-23, Vide memo no. 1305 /I / Admn / 795/ 22 / SJDA, dated 12.08.2022 has been circulated. Last date of the opening of BID was 08.09.2022. Tender section submitted current status of the NIB. One bidder has been participated. Approval taken for re-tender. File placed to Tender section on dated 25.11.2022. Re-tender (2nd call) was floated. One bidder has been participated. 3rd call was floated on 01.03.2023.
8 | Installation advertisement board at 45 nos. LED Light poles at NJP to IOCL underpass. | ------------- | ----------------- | ------------- | --------------- | ------------- | NIB (E-BIDDING) No. 007/ ADMN/ 22-23, Vide memo no. 1306 /I / Admn / 799/ 22 / SJDA, dated 12.08.2022 has been circulated. Last date of the opening of BID was 08.09.2022. Tender section submitted current status of the NIB. One bidder has been participated. Approval taken for re-tender. File placed to Tender section on dated 25.11.2022. Re-tender (2nd call) was floated. No one has been perticipated. 3rd call to be floated.
9 | Installation advertisement board at 32 nos. LED Light poles located at 3rd Mahananda Bridge. | ------------- | ----------------- | -------------- | --------------- | -------------- | NIB (E-BIDDING) No. 009/ ADMN/ 22-23, Vide memo no. 1309 /I / Admn / 796/ 22 / SJDA, dated 12.08.2022 has been circulated. Last date of the opening of BID was 08.09.2022. Tender section submitted current status of the NIB. One bidder has been participated. Approval taken for re-tender. File placed to Tender section on dated 25.11.2022. Re-tender (2nd call) was floated. No one has been perticipated. 3rd call to be floated.
10 | Installation advertisement board at 44 nos. LED Light poles located at 4th Mahananda Bridge, Jyotinagar, Ward No. 04. | -------------- | ------------------ | -------------- | ---------------- | --------------- | NIB (E-BIDDING) No. 008/ ADMN/ 22-23, Vide memo no. 1304 /I / Admn / 797/ 22 / SJDA, dated 12.08.2022 has been circulated. Last date of the opening of BID was 08.09.2022. Tender section submitted current status of the NIB. One bidder has been participated. Approval taken for re-tender. File placed to Tender section on dated 25.11.2022. Re-tender (2nd call) was floated. No one has been perticipated. 3rd call to be floated.
11 | Advertisement display - 5th Mahananda Bridge. | ------------- | --------------- | -------------- | -------------- | ------------- | Fresh Tender to call. File no. I/Admn/ 798 / 2022.
12 | Advertisement display - Bosundhara Abason more, Uttar Kanya to Jorapani Bridge. | ------------- | --------------- | -------------- | -------------- | ------------- | Fresh Tender to call. File no. I/Admn/ 800 / 2022.
13 | Advertisement display - Darjeeling more to Sevin Kingdom. | ------------- | --------------- | -------------- | -------------- | ------------- | Fresh Tender to call. File no. I/Admn/ 794/ 2022.
14 | Advertisement display -LIC Building to Bhaktinagar Check Post. | COLOURS, Siliguri | 1388/Admn/556 / 19/ SJDA, dated 15.10.2020 2nd year renewal given to the agency vide memo no. 1904/ I/Admn/ 556/19 dated 02.11.2021 | 01.10.2021 to 30.09.2022 | Rs. 25,96,000/- (including taxes) | Rs. 21,49,000/- (including taxes) | Outstanding balance amount Rs. 4,47,000/- only to be received from the agency. Renewal period has been over. Last time for payment within 15/01/2023.
15 | Advertisement through 09nos. Unipole structure between road dividers from LIC building (Makhan Bhog) to Bhaktinagar check post | Swastik Ad. Agency, Siliguri | 455/X/Engg/ Elct/ 08 / 19 / SJDA, dated 15.02.2021 | 15.02.2021 to 14.02.2022 | Rs. 4,67,550/-(Excluding taxes) | Rs. 5,51,709/- (including taxes) | After issue of work order, agency has not started the work due to non receipt of permanent NOC from PWD. Now, as per kind order of CEO, SJDA, the agency has started the work.